Salama Brewing Company Oy

Real-Time Cash Flow Dashboard

Technical Specification & Scope

March 2026 | Prepared for Board Review | Cloudberry VC

# 1. Why This Is Needed

On Monday March 23, LivePlan showed Salama ending March at +€10,391 cash. Two days later, the Procountor bank forecast shows cash going negative on March 26 and reaching -€64,138 by March 31. The €74K gap is entirely caused by working capital timing that LivePlan’s monthly accrual model cannot capture.

|  | LivePlan (Monday) | Procountor (Today) |
| --- | --- | --- |
| March end cash | +€10,391 | -€64,138 |
| Tax payment | Not visible | -€30,060 (Mar 25) |
| Loan payment | €14,357/mo | €15,356/mo |
| Timing visibility | Monthly totals only | Daily, to the euro |

LivePlan is useful for strategic scenario planning (Original vs Pessimistic, when to cut). But for a company with €24K starting cash and €170K+ in monthly outflows, you need daily cash visibility. That’s what this dashboard provides.

# 2. What We Build

A new “Cash Position” layer added to the existing Salama Cash Flow Planner dashboard, powered by live Procountor data instead of LivePlan forecasts. The existing scenario planning tabs (Original/Mid/Pessimistic, personnel cuts, cost analysis) remain — we add tactical cash management underneath.

## 2.1 Dashboard Tabs

| Tab | Shows | How It Helps | Priority |
| --- | --- | --- | --- |
| Cash Position | Daily bank balance + 13-week forecast | The Procountor screenshot view, but projected forward | P0 (day 1) |
| Receivables | Who owes money, when it's due, likelihood of on-time payment | Predict actual cash-in timing using DSO history | P0 (day 1) |
| Payables | What's due out, can anything be delayed? | Flag which payments can stretch without damaging supplier relations | P0 (day 1) |
| Working Capital | DSO/DPO/CCC trends, seasonal patterns | Historical analysis to predict forward-looking WC needs | P1 (week 2) |
| Scenario Overlay | Existing Original/Mid/Pessimistic scenarios | Already built — connect to live actuals | P1 (week 2) |
| Alerts | Automatic warnings when cash drops below thresholds | Slack notification when projected cash < €20K | P2 (week 3) |

## 2.2 The 13-Week Rolling Cash Forecast

This is the core deliverable. A 13-week (one quarter) forward-looking cash forecast built from actual Procountor data, not LivePlan assumptions.

How it works:

- Start with today’s actual bank balance (from Procountor bank statement)

- Add all known receivables by their expected payment date (due date adjusted by customer’s actual DSO)

- Subtract all known payables by their due date

- Subtract recurring fixed outflows: loan (€15,356), salary (2x/mo), tax dates, rent

- For weeks beyond known invoices, use the LivePlan scenario forecast (Original/Mid/Pessimistic) as the projection basis

- Result: a daily cash position forecast that’s accurate near-term and scenario-based further out

The key insight: weeks 1-4 are driven by actual invoices already in Procountor. Weeks 5-13 blend into the scenario forecasts. This gives you both tactical precision (this week) and strategic direction (this quarter).

# 3. Data We Pull from Procountor

| Endpoint | What It Gives Us | Key Fields |
| --- | --- | --- |
| GET /invoices | All sales & purchase invoices | Invoice date, due date, amount, status, counterparty, payment info, rows |
| GET /invoices/{id} | Single invoice detail | Full invoice with line items, payment terms, bank account |
| GET /bankstatements | Bank statement list | Statement dates, balances, statement numbers |
| GET /bankstatements/{id}/events | Bank transactions | Individual transactions with dates, amounts, references |
| GET /ledgerreceipts | Accounting vouchers | Journal entries, account codes, amounts, dates |
| POST /reports/accounting | Financial reports | Income statement, balance sheet, cash flow by period |
| GET /businesspartners | Customer/supplier master | Names, IDs, payment terms, contact info |

Rate limits are generous: 60 requests/second in production. A full daily sync of all invoices, bank statements, and ledger data would use perhaps 20-50 API calls. No risk of hitting limits.

# 4. Working Capital Analytics (Backwards-Looking → Forward-Looking)

This is the answer to your question: can we use historical data to predict forward-looking working capital? Yes. Here’s exactly what we’d calculate:

| Metric | What It Measures | Data Source | Breakdown |
| --- | --- | --- | --- |
| DSO (Days Sales Outstanding) | Avg days customers take to pay | Invoice date vs payment date on sales invoices | By customer, by month, trailing 12-month |
| DPO (Days Payable Outstanding) | Avg days Salama takes to pay | Invoice date vs payment date on purchase invoices | By supplier, by month, trailing 12-month |
| Cash Conversion Cycle | DSO - DPO + DIO | Combined from above metrics | Monthly trend, seasonal pattern |
| Receivables Aging | Open AR by age bucket | Unpaid sales invoices vs due date | 0-30, 31-60, 61-90, 90+ days |
| Payables Aging | Open AP by age bucket | Unpaid purchase invoices vs due date | 0-30, 31-60, 61-90, 90+ days |
| Payment Reliability Score | % invoices paid on time per customer | Due date vs actual payment | Per customer, flag slow payers |

## 4.1 How This Predicts Forward-Looking Cash

Example: LivePlan says April revenue is €201,863. That’s meaningless for cash planning. What matters is:

- Kesko pays in ~25 days (DSO from history) → April invoices land in late April/early May

- SOK pays in ~35 days → April revenue arrives mid-May

- Export clients pay in 45-60 days → April revenue arrives June

- Bars/pubs pay in ~40 days → April revenue arrives mid-May

By applying customer-specific DSO to the LivePlan revenue forecast, we convert “€201K in April” into an actual weekly cash-in schedule. Combined with the payables schedule, you get a real cash forecast — not the fiction that LivePlan provides.

## 4.2 Seasonal Patterns

The brewery business is highly seasonal (August peak at €281K revenue, December trough at €154K). Working capital patterns will differ by season — summer months likely have faster collections (bars paying quickly during high season) and higher raw material prepayments. The model captures these patterns from historical data and applies them to the forecast.

# 5. Technical Architecture

Data flow:

Procountor API  →  Python sync script  →  JSON data file  →  HTML Dashboard

- Python script runs daily (cron) or on-demand, authenticates via OAuth2, pulls latest data

- Calculates DSO/DPO/CCC, builds 13-week forecast, writes to a JSON file

- The existing HTML dashboard reads the JSON and renders the new tabs alongside the scenario planner

- No database needed — JSON file is the “database” (invoices + computed metrics)

- Can run 100% locally (no cloud hosting required) or deploy to a simple server for shared access

This keeps it dead simple. No servers, no databases, no infrastructure. Just a script that talks to Procountor and a dashboard that reads the output.

# 6. Implementation Timeline

| When | What | Who |
| --- | --- | --- |
| Day 0 | Salama activates Procountor API (€15.39/mo) | Salama CFO/accountant |
| Day 1 | Register OAuth2 client, get test environment credentials | Developer |
| Day 2-3 | Build data extraction: invoices, bank statements, payments | Developer |
| Day 4-5 | Build working capital analytics engine (DSO/DPO/CCC) | Developer |
| Day 6-7 | Build 13-week rolling forecast model | Developer |
| Day 8-9 | Integrate into existing HTML dashboard (new tabs) | Developer |
| Day 10 | Test against historical data, validate predictions | Developer + Rene |
| Ongoing | Daily auto-refresh via cron job or manual trigger | Automated |

Total: ~10 working days from API activation to live dashboard. The bottleneck is getting Salama to activate the API and provide credentials — the build itself is straightforward.

# 7. Cost Estimate

| Item | Cost | Type |
| --- | --- | --- |
| Procountor API | €15.39/mo + VAT = ~€19.30/mo | Recurring |
| Development (est. 40-60 hrs) | €4,000-6,000 one-time | Or build in-house with Claude |
| Hosting (if needed) | €5-20/mo (simple VPS or serverless) | Optional — can run locally |
| TOTAL YEAR 1 | ~€4,200-6,250 |  |
| TOTAL ONGOING | ~€240-470/yr | API + hosting only |

For context: the €74K gap between LivePlan and reality that we discovered today would pay for 12+ years of this dashboard.

# 8. Immediate Next Steps

- TODAY: Ask Salama if they have an overdraft facility with OP. Cash goes negative tomorrow.

- THIS WEEK: Get Salama to activate Procountor API (€15.39/mo). Takes 5 minutes in their admin panel.

- THIS WEEK: Get OAuth2 credentials and test environment access.

- NEXT WEEK: Start building. P0 tabs (Cash Position, Receivables, Payables) in ~5 days.

- WEEK AFTER: Working capital analytics + scenario overlay. Full dashboard live.

The strategic scenario planner we already have tells you when to make big decisions (cuts, layoffs, bridge financing). This tactical layer tells you whether you can make payroll next Tuesday. You need both.